<Enter PROGRAM/PROJECT > RISK MANAGEMENT PLAN

Note:

Reference template for use

of the Leonardo Spa Electronics Division-Defense Systems BU Suppliers

Box to be deleted

| Prepared by: Department Name Surname | Signature |
| --- | --- |
| Verified by: Department Name Surname | Signature |
| Approved by: Department Name Surname | Signature |

- INDEX OF REVISIONS

| Rev. | Date | Description |
| --- | --- | --- |
| 00 | <Enter date> | First Issue |

INDEX

INDEX OF REVISIONS	3

1	INTRODUCTION	5

1.1	Scope	5

1.2	Applicability	5

1.3	Updating	5

2	REFERENCE DOCUMENTS	5

2.1	Applicable Documents	5

3	PROCESS	6

3.1	Risks Identification	6

3.2	Evaluation	6

3.2.1	Qualitative Evaluation	6

3.2.2	Quantitative Evaluation	6

3.2.3	Probability that the risk occurs	7

3.2.4	Impact of risk	7

3.2.4.1	Impact on schedule	7

3.2.4.2	Impact on costs and cash flow	8

3.2.4.3	Impact on performance	8

3.2.5	Risk Priority Index	9

3.3	Risk treatment	9

3.4	Risk Monitoring and Review	10

4	RISK REGISTER	10

LIST OF TABLES

Table 1 – Quantification of probability	7

Table 2 – Quantification of the impact on time	7

Table 3 – Quantification of the impact on costs and cash flow	8

Table 4 – Quantification of the impact on performance	8

Table 5 – Risk Matrix	9

Table 6 – Risk Register Fields Description	10

# INTRODUCTION

## Scope

This document, issued in accordance with what is defined in doc. PQA004-L-IT-D, describes the methods for the classification, identification, assessment, mitigation and control of the relative risks in the context of supplies for Leonardo Spa - Electronics Division - Defence Systems BU

## Applicability

The document applies to the design, development and implementation of supplies for Leonardo Spa - Electronics Division - Defence Systems BU relating to the Purchase Order / Contract no. <enter order number / contract> of <enter order date>, aimed at the following product:

- < Enter product to which the supply refers >

## Updating

This document will be updated according to the deadlines set by the Purchase Order / Contract and by the document PQA004-L-IT-D.

# REFERENCE DOCUMENTS

## Applicable Documents

| Ref. | Code | Title |
| --- | --- | --- |
|  | EN 9001:2015 | Quality Management Systems Standard |
|  | EN 9100:2018 | Quality Management Systems - Requirements for Aviation, Space and Defence Organizations |
|  | AQAP 2110 ed. D | NATO Quality Assurance Requirements For Design, Development and Production (limited to Risk Management requirements) |
|  | UNI ISO 31000:2009 | Gestione del rischio. Principi e linee guida |
|  | ISO/IEC 31010:2009 | Risk management – Risk assessment techniques |
|  | PQA004-L-IT-D | Requisiti di Qualità per le forniture alla Divisione Sistemi di Difesa di Leonardo S.p.a. |

# PROCESS

The Project Risk Management Process is an interactive process that covers the entire life cycle of the Project; it is structured in sub-processes as briefly illustrated in the following paragraphs.

## Risks Identification

The identification of risks takes place with the support of specific tools (e.g.: Checklists, Historical Data ...) through the analysis of the contractual scenario, of the activities subject to supply and of the related budget. The identified risks can be identified, on the basis of their nature, in operating (technical-industrial, contractual, asset and marketing assets), strategic and financial.

Each identified risk must be described with the use of a metalanguage in terms of causes / events / effects in order to highlight the essential elements for its management with appropriate action plans.

## Evaluation

The first phase of the risk assessment involves the analysis that is divided into:

- qualitative: The qualitative evaluation of the risk consists in determining the degree in which each identified risk may influence (either positively or negatively) the project objectives and milestones, and thus obtain a ranking in terms of their importance and urgency;

- quantitative: The quantitative evaluation of the risk consists in quantifying the Risk Value for each identified risk and the Project Risk Value, in order to define appropriate mitigation actions and protective measures related to the residual project risk.

### Qualitative Evaluation

The qualitative assessment of risks consists in determining the most critical risks that require particular attention by the Program Manager / Risk Manager.

To do this, an analysis is conducted to attribute to each risk a qualitative assessment of the "VERY HIGH", "HIGH", "MEDIUM", "LOW" and "MINIMAL" type that refers both to the probability that it will occur, both to the impact of this on the project / program (in terms of time, cost and performance).

### Quantitative Evaluation

The quantitative risk assessment aims to quantify the economic impact on project / program costs if the risk occurs and, after having included the benefits of mitigation actions in the assessment, to determine which contingency must be set aside to minimize the possibility to have to bear extra costs if the risks should occur.

This quantification is therefore necessary to assess the possible benefits of mitigation actions by comparing the expected value of the risk, pre-and post-mitigation.

Each risk, identified in the final summary of the previous phase, is evaluated in terms of the probability of it occurring and its impact on the program should it be realized and, furthermore, it is classified by assigning it a 'Risk Factor' that allows to examine the priorities of intervention.

### Probability that the risk occurs

To the probability of a risk occurring is assigned a weight according to the following criterion

| Category | % of Probability | Weight assigned |
| --- | --- | --- |
| Very High | P ≥ 70% | 5 |
| High | 50% ≤ P < 70% | 4 |
| Medium | 30% ≤ P < 50% | 3 |
| Low | 10% ≤ P < 30% | 2 |
| Minimal | P < 10% | 1 |

Table 1 – Quantification of probability

### Impact of risk

The impacts on the program due to the occurrence of the risk are divided into three categories, each of which must be considered with its own weight, according to the following indicative tables:

#### Impact on schedule

The individual risk is related, in terms of time, to the duration of the project / program:

| Category | Criteria | Weight |
| --- | --- | --- |
| Critical | Critical delay compared to project baseline (greater than 20%); impact on the major contractual milestones and on delivery dates. May lead to termination of the project. | 5 |
| Severe | Serious delay compared to project baseline (greater than 10% and less than or equal to 20%); slip of contractual milestones without impact on delivery dates. New planning required. | 4 |
| Significant | Major delay in project baseline (greater than 5% and less than or equal to 10%); slip of certain non-critical milestones. | 3 |
| Low | Minor delay in project baseline (less than or equal to 5%); no impact on milestones. New planning preferred. | 2 |
| Negligible | Minimal or no impact on project planning; no impact on milestones and/or schedule changes compensated by margins. No new planning required. | 1 |

Table 2 – Quantification of the impact on time

#### Impact on costs and cash flow

| Category | Criteria | Weight |
| --- | --- | --- |
| Critical | Increase of project costs greater than 10%. Financial charges over 12 months. | 5 |
| Severe | Increase of project costs greater than 5% and less than or equal to 10%. Financial charges between 9 and 12 months. | 4 |
| Significant | Increase of project costs greater than 2% and less than or equal to 5%. Financial charges between 6 and 9 months. | 3 |
| Low | Increase of project costs less than or equal to 2%. Financial charges between 3 and 6 months. | 2 |
| Negligible | Minimal or no impact on project cost (estimated budget is confirmed). Financial charges within 3 months. | 1 |

Table 3 – Quantification of the impact on costs and cash flow

#### Impact on performance

The requirements will not be satisfy, including reliability and maintainability.

| Category | Criteria | Weight |
| --- | --- | --- |
| Critical | May lead to termination of project, due to compromised System operability and failure to achieve performance expected by the Customer. The effects are clearly evident to the Customer. | 5 |
| Severe | Large performance degradation at System level, with impact on the system's functionality and operability. The effects are clearly evident to the Customer. | 4 |
| Significant | Performance degradation at System level, without impacts on the system's functionality and operability. The effects are clearly evident to the Customer. | 3 |
| Low | Minor consequences, degradation with impact only on internal System components: the effects may not be evident to the Customer (or may not be of Customer interest). | 2 |
| Negligible | Minimal or no impact on performance. The effect is not evident to the Customer (or not of Customer interest). | 1 |

Table 4 – Quantification of the impact on performance

### Risk Priority Index

The "Risk Factor" (RPI) represents an ordered classification of risks against the two parameters assessed above (probability and impact) and is defined as follows:

RPI = Probability Index x  Impact on project/program Index

In quantifying the impact, the highest value must be considered among those measured on schedule, costs and performance.

The results of this formula are 6 possible values ​​ that can be weighed in the following way:

Risks

Opportunities

Probability Index (IP)

Impact Index (IP)

Table 5 – Risk Matrix

All risks with a RPI greater or equal to 5 shall be managed with specific treatment actions.

## Risk treatment

Once the risks have been identified and evaluated, they must be treated in order to reduce their potential impact or their probability of occurrence.

The objective of this phase is therefore the identification and choice of the actions to be implemented so as to reduce the probability of occurrence and/or the impact of each risk.

The possible choices to be made during the definition of the treatment strategy and thus during the identification of the most appropriate action plan, are classified as follows:

- mitigation: preventive actions with respect to the risk occurrence, that aim to reduce o remove the causes, reduce the probability of occurrence and/or the effects. They may be classified ex ante as preventive actions if they produce an effect on the probability index or as protective actions if they produce an effect on the impact index;

- recovery/corrective: corrective actions to be implemented upon risk occurrence so as to further reduce the consequences;

- transfer: actions that aim to reduce or eliminate the risk, shifting it to other parties (Customers, Suppliers, including Insurance Companies) and transferring the consequences (impact);

- acceptance: if it is not possible to manage the risk and no specific actions can be implemented. The accepted risk is subject to periodic surveillance.

The mitigation actions may remove common causes to the occurrence of various risks and must therefore be conducted, if possible, transversely, so as to mitigate multiple risks at project and portfolio level.

## Risk Monitoring and Review

An effective Risk Management process must be based on careful and constant monitoring activity of trends and evolution of risks.

The update of the Risk Sheet must be done periodically, at least on a quarterly basis and/or in case of Risk Review and/or for other necessities associated to the project or to company needs (e.g. budget/forecast).

The objective of this phase is to:

- verify the implementation and effectiveness of the mitigation plan, including any new actions;

- update the risk status, its probability of occurrence and its cost;

- identify and evaluate any new risks (emergent).

# RISK REGISTER

The Risk Register is defined (as per attachment <Enter file name to be issued (eg: Risk Report.xlsx)>) as a summary table reporting all the risks identified and monitored during the program and must be considered confidential between the Supplier and Leonardo Spa - Electronics Division - Defence Systems BU.

The report contains the following fields:

| Fields | Description |
| --- | --- |
| Risk ID | Code that distinctly identifies the risk in the Risk Register |
| Risk Cause | Description of the cause of the risk |
| Risk Event | Description of the risk event that may occur |
| Risk Effects | Description of the effects deriving from the risk |
| Milestone/Date of Impact | Description and relevant date of the affected project milestone/objective |
| RPI | Risk Priority Index or Risk Score or Risk Factor |
| Risk Owner | Name of the person or department in charge of managing the risk |
| Mitigation Actions Description | Description of the actions for risk reduction |
| End Date | End date of the mitigation action (it cannot be subsequent to the date of the risk affected milestone) |
| Progress Description | Description of the action progress |

Table 6 – Risk Register Fields Description